## Backlog
Priority | State | I want <functionnalities> | to get a certain value | Estimation (hours) | Comments
High | In progress | to force of variables | to put a special value | 10
High | To do | to get the variables' state | to verify whether the variable is forced | 5
Low | To do | to have a timestamp with correct date | to watch when the value's variable has been uptaded | 2
High | Done | to search when user make a copy of text | To have the list the variable without paste | 5
High | Done | to have a window to left-bottom | to see always the value and variables | 3
Medium | In progress | to write a variable without lag | to write the text smoothly | 2
High | Done | to edit the copied variable | to change the variable when we need | 4
High | Done | to have the exhaustive list of variables | to be able to shearch a variable | 4
Medium | Done | to have a button, which refresh the variables list | to get the new list of variables | 3
High | Done | to refresh automatically the variables' value | to watch the changes of values | 4
High | Done | to change the background color of value | to watch a change | 3
Medium | Done | to show the information | to watch the different problem from application | 2